## Sheet1
Task | Estimated Time to Complete(h) | Real Time to Complete (h) | Raffi | Duncan | Matthew | Ethan | Omer | Date of Team Meating
1.1 Overview | 1 | 1 | 1
1.2 SDLC | 1 | 1 | 1
1.3 WBS | 4 | 4 | 4
1.4 Gantt Chart | 3 | 3 | 3
2.1.1 Group Meeting | 2.5 | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 22nd Jan
2.1.2 Do Tasks (With Testing) | Total Estimated Task Time (7) | Total Actual Task Time (8)
Task 1) Build Prototype | 5 | 6 |  | 3 | 3
Task 2) Topic Names | 2 | 2 |  |  |  |  | 2
2.1.4 Usability | 1 | 1 | 1
|  |  | Raffi | Duncan | Matthew B. | Ethan | Omer
2.2.1 Group Meeting | 1.2 | 1.2 |  | 0.3 | 0.3 | 0.3 | 0.3 | 24th Jan
2.2.2 Do Tasks (With Testing) | Total Estimated Task Time (7) | Total Actual Task Time (8)
Task 1) Adding Topics Functionality | 3 | 3 |  |  | 3
Task 2) Library Files and Google Search | 2 | 2 |  | 2
Task 3) Build Wolfram Java Class | 2 | 3 |  |  |  | 3
2.2.4 Usability | 1 | 1 |  | 1
|  |  | Raffi | Duncan | Matthew B. | Ethan | Omer
2.3.1 Group Meeting | 1.5 | 1.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 28th Jan
2.3.2 Do Tasks (With Testing) | Total Estimated Task Time(5.5) | Total Actual Task Time (6.5)
Task 1) Defining Topics | 4 | 4 |  |  | 1 |  | 3
Task 2) Store questions codebot doesn't know | 0.5 | 0.5 |  | 0.5
Task 3) Design method for approximate string matching | 1 | 2 |  |  |  | 2
2.3.4 Usability | 1 | 1 |  | 1
|  |  | Raffi | Duncan | Matthew B. | Ethan | Omer
2.4.1 Group Meeting | 1.5 | 1.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 31st Jan
2.4.2 Do Tasks (With Testing) | Total Estimated Task Time (19) | Total Actual Task Time (20.5)
Task 1) Define Sub-Topics | 15 | 15.5 | 4.5 |  | 5 |  | 6
Task 2) Implementing Sub-Topics | 3 | 2 |  |  | 2
Task 3) Implement approx. string matching | 1 | 3 |  |  |  | 3
2.4.4 Usability | 1 | 1 |  |  |  | 1
|  |  | Raffi | Duncan | Matthew B. | Ethan | Omer
2.5.1 Group Meeting | 1.5 | 1.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 4th Feb
2.5.2 Do Tasks (With Testing) | Total Estimated Time (4) | Total Actual Time (4)
Task 1) Generate Output | 1 | 1 |  |  | 1
Task 2) Documentation | 3 | 3 |  | 1 | 1 | 1
2.5.4 Usability | 1 | 1 |  | 1
TOTAL | 64.7 | 69.2 | 15.9 | 11.2 | 17.7 | 11.7 | 12.7